## Sheet2
| WEEK 1 |  | WEEK 2 |  | WEEK 3 |  | WEEK 4 |  | WEEK 5 |  | WEEK 6 |  | WEEK 7
| May 6 - May 12 |  | May 13 - May 19 |  | May 20 - May 26 |  | May 27 - Jun 2 |  | Jun 3 - Jun 9 |  | Jun 10 - Jun 16 |  | Jun 17 - Jun 23
Overview |  | Groups definition |  | Deliverables (21/May) |  | Data partition |  | Deliverable: Report 1 (4/Jun) |  | Loss function |  | Deliverable: Report 2 (18/Jun)
Goals |  | Project topic selection |  | • Request Project Proposal |  | Data augmentation |  | • Data collection technique |  | Optimizer function |  | • Data augmentation process
Git / GitHub review | [5 empty] | Dataset preparation |  | • Data annotation process |  | GitHub repository update |  | • Neural Net building process
|  |  |  | Data collection |  | GitHub repository update |  |  |  | Project board update
|  |  |  | Data annotation |  | Project board update |  | Neural Net model building |  |  |  | NL Model training
|  |  |  | GitHub repository creation |  |  |  | Classification / Regression |  |  |  | Performance analysis
Convolutional Neural Net
|  |  |  | Milestone: |  | Milestone | [5 empty] | Milestone
|  |  |  | Labeled pictures delivery |  | Final dataset delivery | [5 empty] | Neural Network Model
| INTRODUCTION |  | PLANNING |  | DATA PREPARATION |  | DATA AUGMENTATION |  | NEURAL NET BUILDING |  | NEURAL NET BUILDING |  | NEURAL NET TRAINING
| WEEK 9 |  | WEEK 10 |  | WEEK 11 |  | WEEK 12 |  | WEEK 13 |  | WEEK 14 |  | WEEK 15
| Jul 1 - Jul 7 |  | Jul 8 - Jul 14 |  | Jul 15 - Jul 21 |  | Jul 22 - Jul 28 |  | Jul 29 - Aug 4 |  | Aug 5 - Aug 11 |  | Aug 12 - Aug 18
Deliverable: Report 3 (2/Jul) |  | Server configuration |  | Deliverable: Report 4 (16/Jul) |  | Publishing and configuration |  | Deliverable: Report 5 (30/Jul) |  | Final presentation |  | Final Report document delivery
• Neural Net training process |  | API Rest Service development |  | • Neural Net testing process |  | BE / FE Integration |  | • Deployment documentation |  | Demo
|  | GitHub repository update |  |  |  | End-to-End tests
Predictions on TEST dataset |  | Documentation update |  | User Interface development |  | GitHub repository update |  | Final report preparation |  | GitHub repository update
Saving the model |  | Project board update |  | GitHub repository update |  | Documentation update |  | Final presentation preparation |  | Documentation update
Real time prediction testing |  |  |  | Documentation update |  | Project board update |  | Demo preparation |  | Project board update
GitHub repository update |  |  |  | Project board update
Milestone: |  |  |  | Milestone: |  | Milestone: |  | Milestone:
Compiled model |  |  |  | Site and API service running |  | Project integration |  | Final documentation
| NEURAL NET TESTING |  | BACKEND DEVELOPMENT |  | FRONTEND DEVELOPMENT |  | DEPLOYMENT |  | FINAL REPORT PREPARATION |  | FINAL PRESENTATION |  | FINAL REPORT DELIVERY